## Index
Test Case Result Modules-Wise
Module\Status | Count Of Test Case(Steps) |  |  |  |  | % Completed
| Pass | Fail | Blocked | Not Executed | Total
SMART-Export | 21 | 4 | 1 | 0 | 26 | 100%
Total | 21 | 4 | 1 | 0 | 26 | 100%
[5 empty] | % Incompleted | 0%

## Test Scenerios
US# | US | TC# | Scenario
User Story: SMART-Export As a SMART User, I want to have the ability to understand Export functionality of any Report | TC01 | Verify Home screen after login into Application.
| TC02 | Verify Export button (When no items are selected)
| TC03 | Verify Clicking Export button should open the “Select an Export Type ...“ small modal with Export options, Cancel and Send buttons
| TC04 | Verify User able to Export items in a selected format
| TC05 | Verify Export button when records are selected by user
| TC06 | Verify in "Export" button counter should be increases/decrese by 1 each time when user select/Deselect any record from the AgGrid/Carousel
| TC07 | Verify in As a counter of selected items - Clicking the export button in this state should expand the secondary export actions (Export Selected and Reset Selected) and the Cancel button
| TC08 | Verify Cancel button Functionality | WEB-7504
| TC09 | Verify the secondary Export FAB buttons are smaller than the primary FAB buttons and expand up from the primary Export FAB button.
| TC10 | Verify Reset Functionality
| TC11 | Verify the tooltip for Reset Export button should be “Reset Selected“
| TC12 | Verify The text for the tooltip of "Close Export FAB" button is “Cancel“
| TC13 | Verify on clicking the "Cancel" button in the small modal with Export options should close the window
Chart Export
| TC14 | Verify Chart card
| TC15 | Verify Chart Export functionality
| TC16 | Verify User able to Export chart in Excel format
| TC17 | Verify User able to Export chart in JPEG format
| TC18 | Verify User able to Export chart in PNG format
| TC19 | Verify User able to Export chart in PDF format
| TC20 | Verify Updated chart should be Exported after user updates any Legends
| TC21 | Verify Updated chart should be Exported after user drill down in any pie chart
| TC22 | Verify the Content of Excel exported file
Pivot Export
| TC23 | Verify User able to Export Pivot data
| TC24 | Verify The “Select an Export Type ...“ small modal has a preview of the export. It should cycle as the user changes the export type
| TC25 | Verify Exported video file should not be exported as Image | SMRT-8045
| TC26 | Verify Help Center link in exported excels and PPT should be redirects to new help link | SMRT-7944
| Required ? | Verify If user has selected any Bar from Bar chart then while export file should be Exported as selected Bar
Verify The “Select an Export Type ...“ small modal has a preview of the export. It should cycle as the user changes the export type

## SMART- Export
| Name: | Export in new UI |  |  | Regression
| Description: | As a smart user can Export selected report |  |  | Test Date:
| Product: | SMART |  |  | Tester Name: | Sumit Rana
| Feature: | Export Functionality |  |  | OS/Browser: | FF , IE11 , Chrome
| Requirement Covered: |  |  |  | Test Result
| Last Update of this Document: | 2020-06-17 |  |  | Pass | 21
| Estimated Run Time: |  |  |  | Fail | 4
| Author: | Numerator QA Team |  |  | Blocked | 1
| Last Run: |  |  |  | Not Executed | 0
| Test Cases Passed: | 21
| Test Cases Failed: | 4
| Test Cases Blocked: | 1
| Test Cases Not Executed: | 0
User Story: SMART- Export in new Ui
Description : As a SMART User, I want to have the ability to understand the Export functionality in Redesign
US:WEB-7387_TC 01 | Verify Home screen after login into Application. |  |  |  | Test Case Status: | Pass | image
Precondition | User have SMART URL with valid Login credential.
Step | Action | Expected Result | Dataset | Requirement # | Step Result | Comments
1 | Verify Home screen. | User should on Home screen of the application. Home screen should contain below section: 1. Numerator logo on Top Left side of screen 2. Report list on left side 3. Total creatives chart 4. Search & Export button on left side 5. Schedule and Reset button 6. Saved search list 7. Breadcrumb below creative summary chart 8. Summary tag as per current date filter 9. Field options, Export & Search options button on Right bottom side |  |  | Pass
END
US:WEB-7387_TC 02 | Verify Export button (When no items are selected) |  |  |  | Test Case Status: | Pass
Precondition | User have SMART URL with valid Login credential.
Step | Action | Expected Result | Dataset | Requirement # | Step Result | Comments
1 | Verify Home screen. | User should on Home screen of the application. Home screen should contain below section: 1. Numerator logo on Top Left side of screen 2. Report list on left side 3. Total creatives chart 4. Search & Export button on left side 5. Schedule and Reset button 6. Saved search list 7. Breadcrumb below creative summary chart 8. Summary tag as per current date filter 9. Field options, Export & Search options button on Right bottom side |  |  | Pass
2 | Verify Export button | 1. Export button should be displayed in Sapphire color |  |  | Pass
3 | Verify Tooltip of Export button | 1. Tooltip should be "Export results" 2. Tooltip color should be in Sapphire color with White text |  |  | Pass
END
US:WEB-7387_TC 03 | Verify Clicking Export button should open the “Select an Export Type ...“ small modal with Export options, Cancel and Send buttons |  |  |  | Test Case Status: | Pass
Precondition | User have SMART URL with valid Login credential.
Step | Action | Expected Result | Dataset | Requirement # | Step Result | Comments
1 | Verify Home screen. | User should on Home screen of the application. Home screen should contain below section: 1. Numerator logo on Top Left side of screen 2. Report list on left side 3. Total creatives chart 4. Search & Export button on left side 5. Schedule and Reset button 6. Saved search list 7. Breadcrumb below creative summary chart 8. Summary tag as per current date filter 9. Field options, Export & Search options button on Right bottom side |  |  | Pass
2 | Verify in Normal phase - "Export " should be displayed only when no items are selected for export | User should be able to see the "Export " button when no items are selected for export |  |  | Pass
3 | Verify on clicking the "Export " button should open the “Select an Export Type ...“ small modal with Export options , Cancel and Send buttons | User should be able to open a small modal window on clicking "Export " button with Export options, cancel and Send buttons |  |  | Pass
END
US:WEB-7387_TC 04 | Verify User able to Export items in a selected format |  |  |  | Test Case Status: | Pass
Precondition | User have SMART URL with valid Login credential.
Step | Action | Expected Result | Dataset | Requirement # | Step Result | Comments
1 | Verify Home screen. | User should on Home screen of the application. Home screen should contain below section: 1. Numerator logo on Top Left side of screen 2. Report list on left side 3. Total creatives chart 4. Search & Export button on left side 5. Schedule and Reset button 6. Saved search list 7. Breadcrumb below creative summary chart 8. Summary tag as per current date filter 9. Field options, Export & Search options button on Right bottom side |  |  | Pass
2 | Select "Export" Button | User should be able to open a small modal window on clicking "Export " button with Export options, cancel and Send buttons |  |  | Pass
3 | Select any Export type from the modal window and click the "Send" button | All items should be exported as per the selected export type by the user |  |  | Pass
END
US:WEB-7387_TC 05 | Verify Export button when records are selected by user |  |  |  | Test Case Status: | Pass
Precondition | User have SMART URL with valid Login credential.
Step | Action | Expected Result | Dataset | Requirement # | Step Result | Comments
1 | Verify Home screen. | User should on Home screen of the application. Home screen should contain below section: 1. Numerator logo on Top Left side of screen 2. Report list on left side 3. Total creatives chart 4. Search & Export button on left side 5. Schedule and Reset button 6. Saved search list 7. Breadcrumb below creative summary chart 8. Summary tag as per current date filter 9. Field options, Export & Search options button on Right bottom side |  |  | Pass
2 | Select any record from the AgGrid | Selected items Count(numbers) should be displayed on Export button for i.e "2 items" |  |  | Pass
END
US:WEB-7387_TC 06 | Verify in "Export" button counter should be increases/decrese by 1 each time when user select/Deselect any record from the AgGrid/Carousel |  |  |  | Test Case Status: | Pass
Precondition | User have SMART URL with valid Login credential.
Step | Action | Expected Result | Dataset | Requirement # | Step Result | Comments
1 | Verify Home screen. | User should on Home screen of the application. Home screen should contain below section: 1. Numerator logo on Top Left side of screen 2. Report list on left side 3. Total creatives chart 4. Search & Export button on left side 5. Schedule and Reset button 6. Saved search list 7. Breadcrumb below creative summary chart 8. Summary tag as per current date filter 9. Field options, Export & Search options button on Right bottom side |  |  | Pass
2 | Select multiple records from the AgGrid/Carousel | 1. Selected items Count(numbers) should be displayed on Export button for i.e "2 items" 2. Number of counts should be increases by 1 every time on export button when user selects a new record from AgGrid/Carousel |  |  | Pass
4 | De- select the records from AgGrid/Carousel | Number of counts should be decreases by 1 every time on export button when user de-selects a new record from AgGrid/Carousel |  |  | Pass
END
US:WEB-7387_TC 07 | Verify in As a counter of selected items - Clicking the export button in this state should expand the secondary export actions (Export Selected and Reset Selected) and the Cancel button |  |  |  | Test Case Status: | Fail
Precondition | User have SMART URL with valid Login credential.
Step | Action | Expected Result | Dataset | Requirement # | Step Result | Comments
1 | Verify Home screen. | User should on Home screen of the application. Home screen should contain below section: 1. Numerator logo on Top Left side of screen 2. Report list on left side 3. Total creatives chart 4. Search & Export button on left side 5. Schedule and Reset button 6. Saved search list 7. Breadcrumb below creative summary chart 8. Summary tag as per current date filter 9. Field options, Export & Search options button on Right bottom side |  |  | Pass
2 | Select any record from the AgGrid | Selected items Count(numbers) should be displayed on Export button for i.e "2 items" |  |  | Pass
3 | Click on the "Export Selected" button | 1. Clicking on "Export Selected" button, it expands the secondary export action button "Export Selected" & "Reset Selected" 2. "Export Selected" button should be in green color with "Export Selected" tooltip 3. "Reset Selected" button should be in green color with "Reset Selected" tooltip 4. "Export" button should be changed in to "Cancel" button 5. "Cancel" button should be in green color with "Cancel" tooltip |  |  | Fail | Not able to test due to WEB-7504
END
US:WEB-7387_TC 08 | Verify Cancel button Functionality |  |  |  | Test Case Status: | Blocked
Precondition | User have SMART URL with valid Login credential.
Step | Action | Expected Result | Dataset | Requirement # | Step Result | Comments
1 | Verify Home screen. | User should on Home screen of the application. Home screen should contain below section: 1. Numerator logo on Top Left side of screen 2. Report list on left side 3. Total creatives chart 4. Search & Export button on left side 5. Schedule and Reset button 6. Saved search list 7. Breadcrumb below creative summary chart 8. Summary tag as per current date filter 9. Field options, Export & Search options button on Right bottom side |  |  | Pass
2 | Select any record from the AgGrid | Selected items Count(numbers) should be displayed on Export button for i.e "2 items" |  |  | Pass
3 | Click on the "Export Selected" button | 1. Clicking on "Export Selected" button, it expands the secondary export action button "Export Selected" & "Reset Selected" 2. "Export Selected" button should be in green color with "Export Selected" tooltip 3. "Reset Selected" button should be in green color with "Reset Selected" tooltip 4. "Export" button should be changed in to "Cancel" button 5. "Cancel" button should be in green color with "Cancel" tooltip |  |  | Blocked
4 | Click on "Cancel" button | 1. Secondary actions button should be removed(should be hidden) 2. Cancel button should be changed in to "Export selected" button |  |  | Blocked
END
US:WEB-7387_TC 09 | Verify the Secondary Export buttons are smaller than the primary buttons |  |  |  | Test Case Status: | Pass
Precondition | User have SMART URL with valid Login credential.
Step | Action | Expected Result | Dataset | Requirement # | Step Result | Comments
1 | Verify Home screen. | User should on Home screen of the application. Home screen should contain below section: 1. Numerator logo on Top Left side of screen 2. Report list on left side 3. Total creatives chart 4. Search & Export button on left side 5. Schedule and Reset button 6. Saved search list 7. Breadcrumb below creative summary chart 8. Summary tag as per current date filter 9. Field options, Export & Search options button on Right bottom side |  |  | Pass
2 | Select any record from the AgGrid | Selected items Count(numbers) should be displayed on Export button for i.e "2 items" |  |  | Pass
3 | Click on the "Export Selected" button | 1. Clicking on "Export Selected" button, it expands the secondary export action button "Export Selected" & "Reset Selected" 2. "Export Selected" button should be in green color with "Export Selected" tooltip 3. "Reset Selected" button should be in green color with "Reset Selected" tooltip 4. "Export" button should be changed in to "Cancel" button 5. "Cancel" button should be in green color with "Cancel" tooltip |  |  | Pass
4 | Verify the secondary Export buttons are smaller than the primary buttons. | User should notice that the secondary Export buttons are smaller than the primary buttons |  |  | Pass
END
US:WEB-7387_TC 10 | Verify Reset Functionality |  |  |  | Test Case Status: | Pass
Precondition | User have SMART URL with valid Login credential.
Step | Action | Expected Result | Dataset | Requirement # | Step Result | Comments
1 | Verify Home screen. | User should on Home screen of the application. Home screen should contain below section: 1. Numerator logo on Top Left side of screen 2. Report list on left side 3. Total creatives chart 4. Search & Export button on left side 5. Schedule and Reset button 6. Saved search list 7. Breadcrumb below creative summary chart 8. Summary tag as per current date filter 9. Field options, Export & Search options button on Right bottom side |  |  | Pass
2 | Select any record from the AgGrid | Selected items Count(numbers) should be displayed on Export button for i.e "2 items" |  |  | Pass
3 | Click on the "Export Selected" button | 1. Clicking on "Export Selected" button, it expands the secondary export action button "Export Selected" & "Reset Selected" 2. "Export Selected" button should be in green color with "Export Selected" tooltip 3. "Reset Selected" button should be in green color with "Reset Selected" tooltip 4. "Export" button should be changed in to "Cancel" button 5. "Cancel" button should be in green color with "Cancel" tooltip |  |  | Pass
4 | Click on the "Reset Selected" button | 1. All the selected record should reset 2. Export button should be in normal view (not as "1 item selected") 3. Secondary button should closed |  |  | Pass
END
US:WEB-7387_TC 11 | Verify the tooltip for Reset Export button should be “Reset Selected“ |  |  |  | Test Case Status: | Pass
Precondition | User have SMART URL with valid Login credential.
Step | Action | Expected Result | Dataset | Requirement # | Step Result | Comments
1 | Verify Home screen. | User should on Home screen of the application. Home screen should contain below section: 1. Numerator logo on Top Left side of screen 2. Report list on left side 3. Total creatives chart 4. Search & Export button on left side 5. Schedule and Reset button 6. Saved search list 7. Breadcrumb below creative summary chart 8. Summary tag as per current date filter 9. Field options, Export & Search options button on Right bottom side |  |  | Pass
2 | Select any record from the AgGrid | Selected items Count(numbers) should be displayed on Export button for i.e "2 items" |  |  | Pass
3 | Click on the "Export Selected" button | 1. Clicking on "Export Selected" button, it expands the secondary export action button "Export Selected" & "Reset Selected" 2. "Export Selected" button should be in green color with "Export Selected" tooltip 3. "Reset Selected" button should be in green color with "Reset Selected" tooltip 4. "Export" button should be changed in to "Cancel" button 5. "Cancel" button should be in green color with "Cancel" tooltip |  |  | Pass
5 | Hover on the "Reset Export" button | User should be able to see the tooltip "Reset Selected" on Reset Export button |  |  | Pass
END
US:WEB-7387_TC 12 | Verify The text for the tooltip of "Close Export " button is “Cancel“ |  |  |  | Test Case Status: | Fail
Precondition | User have SMART URL with valid Login credential.
Step | Action | Expected Result | Dataset | Requirement # | Step Result | Comments
1 | Verify Home screen. | User should on Home screen of the application. Home screen should contain below section: 1. Numerator logo on Top Left side of screen 2. Report list on left side 3. Total creatives chart 4. Search & Export button on left side 5. Schedule and Reset button 6. Saved search list 7. Breadcrumb below creative summary chart 8. Summary tag as per current date filter 9. Field options, Export & Search options button on Right bottom side |  |  | Pass
2 | Select any record from the report for Export | User should be able to see "Selected for Export" button when records are selected |  |  | Pass
3 | Click on the "Selected for Export" button | User should be able to see that on clicking the "Selected for Export" button, it expands the secondary export action button "Export Sm", "Reset Export" and "Close Export" button |  |  | Pass
4 | Hover on the "Close Export" button | User should be able to see the tooltip with text "Cancel" |  |  | Fail
END
US:WEB-7387_TC 13 | Verify on clicking the "Cancel" button in the small modal with Export options should close the window |  |  |  | Test Case Status: | Pass
Precondition | User have SMART URL with valid Login credential.
Step | Action | Expected Result | Dataset | Requirement # | Step Result | Comments
1 | Verify Home screen. | User should on Home screen of the application. Home screen should contain below section: 1. Numerator logo on Top Left side of screen 2. Report list on left side 3. Total creatives chart 4. Search & Export button on left side 5. Schedule and Reset button 6. Saved search list 7. Breadcrumb below creative summary chart 8. Summary tag as per current date filter 9. Field options, Export & Search options button on Right bottom side |  |  | Pass
2 | Verify Export button is fixed on the bottom right of the screen | User should be able to see the Export button on the bottom right of the screen |  |  | Pass
3 | Select "Export " Button | User should be able to open a small modal window on clicking "Export " button with Export options, cancel and Send buttons |  |  | Pass
4 | Verify on clicking the "Cancel" button in the small modal with Export options should close the window | On clicking the "Cnacel" button should close the modal window with the Export options |  |  | Pass
END
US:WEB-7387_TC 14 | Verify Chart card |  |  |  | Test Case Status: | Pass
Precondition | User have SMART URL with valid Login credential.
Step | Action | Expected Result | Dataset | Requirement # | Step Result | Comments
1 | Verify Home screen. | User should on Home screen of the application. Home screen should contain below section: 1. Numerator logo on Top Left side of screen 2. Report list on left side 3. Total creatives chart 4. Search & Export button on left side 5. Schedule and Reset button 6. Saved search list 7. Breadcrumb below creative summary chart 8. Summary tag as per current date filter 9. Field options, Export & Search options button on Right bottom side |  |  | Pass
2 | Verify Chart card | User should be able to see following things on Chart 1. Title of chart 2. Expand,Export & Schedule button on right side 3. Chart graph 4. Legends on Below side 5. Date Range and "Numerator" text on Bottom |  |  | Pass
END
US:WEB-7387_TC 15 | Verify Chart Export functionality |  |  |  | Test Case Status: | Pass
Precondition | User have SMART URL with valid Login credential.
Step | Action | Expected Result | Dataset | Requirement # | Step Result | Comments
1 | Verify Home screen. | User should on Home screen of the application. Home screen should contain below section: 1. Numerator logo on Top Left side of screen 2. Report list on left side 3. Total creatives chart 4. Search & Export button on left side 5. Schedule and Reset button 6. Saved search list 7. Breadcrumb below creative summary chart 8. Summary tag as per current date filter 9. Field options, Export & Search options button on Right bottom side |  |  | Pass
2 | Verify Chart card | User should be able to see following things on Chart 1. Title of chart 2. Expand,Export & Schedule button on right side 3. Chart graph 4. Legends on Below side 5. Date Range and "Numerator" text on Bottom |  |  | Pass
3 | Click on Export icon | User should be able to see following things 1. Download Excel 2. Download JPEG 3. Download PNG 4. Download PDF |  |  | Pass
END
US:WEB-7387_TC 16 | Verify User able to Export chart in Excel format |  |  |  | Test Case Status: | Pass
Precondition | User have SMART URL with valid Login credential.
Step | Action | Expected Result | Dataset | Requirement # | Step Result | Comments
1 | Verify Home screen. | User should on Home screen of the application. Home screen should contain below section: 1. Numerator logo on Top Left side of screen 2. Report list on left side 3. Total creatives chart 4. Search & Export button on left side 5. Schedule and Reset button 6. Saved search list 7. Breadcrumb below creative summary chart 8. Summary tag as per current date filter 9. Field options, Export & Search options button on Right bottom side |  |  | Pass
2 | Verify Chart card | User should be able to see following things on Chart 1. Title of chart 2. Expand,Export & Schedule button on right side 3. Chart graph 4. Legends on Below side 5. Date Range and "Numerator" text on Bottom |  |  | Pass
3 | Click on Export icon | User should be able to see following things 1. Download Excel 2. Download JPEG 3. Download PNG 4. Download PDF |  |  | Pass
4 | Click on "Download Excel" option | 1. File should be Exported in Excel format 2. Option list should be closed |  |  | Pass
END
US:WEB-7387_TC 17 | Verify User able to Export chart in JPEG format |  |  |  | Test Case Status: | Pass
Precondition | User have SMART URL with valid Login credential.
Step | Action | Expected Result | Dataset | Requirement # | Step Result | Comments
1 | Verify Home screen. | User should on Home screen of the application. Home screen should contain below section: 1. Numerator logo on Top Left side of screen 2. Report list on left side 3. Total creatives chart 4. Search & Export button on left side 5. Schedule and Reset button 6. Saved search list 7. Breadcrumb below creative summary chart 8. Summary tag as per current date filter 9. Field options, Export & Search options button on Right bottom side |  |  | Pass
2 | Verify Chart card | User should be able to see following things on Chart 1. Title of chart 2. Expand,Export & Schedule button on right side 3. Chart graph 4. Legends on Below side 5. Date Range and "Numerator" text on Bottom |  |  | Pass
3 | Click on Export icon | User should be able to see following things 1. Download Excel 2. Download JPEG 3. Download PNG 4. Download PDF |  |  | Pass
4 | Click on "Download JPEG" option | 1. File should be Exported in JPEG format 2. Option list should be closed |  |  | Pass
END
US:WEB-7387_TC 18 | Verify User able to Export chart in PNG format |  |  |  | Test Case Status: | Pass
Precondition | User have SMART URL with valid Login credential.
Step | Action | Expected Result | Dataset | Requirement # | Step Result | Comments
1 | Verify Home screen. | User should on Home screen of the application. Home screen should contain below section: 1. Numerator logo on Top Left side of screen 2. Report list on left side 3. Total creatives chart 4. Search & Export button on left side 5. Schedule and Reset button 6. Saved search list 7. Breadcrumb below creative summary chart 8. Summary tag as per current date filter 9. Field options, Export & Search options button on Right bottom side |  |  | Pass
2 | Verify Chart card | User should be able to see following things on Chart 1. Title of chart 2. Expand,Export & Schedule button on right side 3. Chart graph 4. Legends on Below side 5. Date Range and "Numerator" text on Bottom |  |  | Pass
3 | Click on Export icon | User should be able to see following things 1. Download Excel 2. Download JPEG 3. Download PNG 4. Download PDF |  |  | Pass
4 | Click on "Download PNG" option | 1. File should be Exported in PNG format 2. Option list should be closed |  |  | Pass
END
US:WEB-7387_TC 19 | Verify User able to Export chart in PDF format |  |  |  | Test Case Status: | Pass
Precondition | User have SMART URL with valid Login credential.
Step | Action | Expected Result | Dataset | Requirement # | Step Result | Comments
1 | Verify Home screen. | User should on Home screen of the application. Home screen should contain below section: 1. Numerator logo on Top Left side of screen 2. Report list on left side 3. Total creatives chart 4. Search & Export button on left side 5. Schedule and Reset button 6. Saved search list 7. Breadcrumb below creative summary chart 8. Summary tag as per current date filter 9. Field options, Export & Search options button on Right bottom side |  |  | Pass
2 | Verify Chart card | User should be able to see following things on Chart 1. Title of chart 2. Expand,Export & Schedule button on right side 3. Chart graph 4. Legends on Below side 5. Date Range and "Numerator" text on Bottom |  |  | Pass
3 | Click on Export icon | User should be able to see following things 1. Download Excel 2. Download JPEG 3. Download PNG 4. Download PDF |  |  | Pass
4 | Click on "Download PDF" option | 1. File should be Exported in PDF format 2. Option list should be closed |  |  | Pass
END
US:WEB-7387_TC 20 | Verify Updated chart should be Exported after user updates any Legends |  |  |  | Test Case Status: | Pass
Precondition | User have SMART URL with valid Login credential.
Step | Action | Expected Result | Dataset | Requirement # | Step Result | Comments
1 | Verify Home screen. | User should on Home screen of the application. Home screen should contain below section: 1. Numerator logo on Top Left side of screen 2. Report list on left side 3. Total creatives chart 4. Search & Export button on left side 5. Schedule and Reset button 6. Saved search list 7. Breadcrumb below creative summary chart 8. Summary tag as per current date filter 9. Field options, Export & Search options button on Right bottom side |  |  | Pass
2 | Verify Chart card | User should be able to see following things on Chart 1. Title of chart 2. Expand,Export & Schedule button on right side 3. Chart graph 4. Legends on Below side 5. Date Range and "Numerator" text on Bottom |  |  | Pass
3 | Deselect any Legend from list | 1. Deselected legend should be display in Gray color 2. Chart should be updated according to it |  |  | Pass
4 | Click on Export icon | User should be able to see following things 1. Download Excel 2. Download JPEG 3. Download PNG 4. Download PDF |  |  | Pass
5 | Export all the option one by one to verify file should be Exported in each format | 1. File should be Exported in each format 2. Option list should be closed |  |  | Pass
END
US:WEB-7387_TC 21 | Verify Updated chart should be Exported after user drill down in any pie chart |  |  |  | Test Case Status: | Pass
Precondition | User have SMART URL with valid Login credential.
Step | Action | Expected Result | Dataset | Requirement # | Step Result | Comments
1 | Verify Home screen. | User should on Home screen of the application. Home screen should contain below section: 1. Numerator logo on Top Left side of screen 2. Report list on left side 3. Total creatives chart 4. Search & Export button on left side 5. Schedule and Reset button 6. Saved search list 7. Breadcrumb below creative summary chart 8. Summary tag as per current date filter 9. Field options, Export & Search options button on Right bottom side |  |  | Pass
2 | Verify Chart card | User should be able to see following things on Chart 1. Title of chart 2. Expand,Export & Schedule button on right side 3. Chart graph 4. Legends on Below side 5. Date Range and "Numerator" text on Bottom |  |  | Pass
3 | Click on any Wedges from list | 1. Pie chart should be Drill down 2. Updated pie chart should be displayed |  |  | Pass
4 | Click on Export icon | User should be able to see following things 1. Download Excel 2. Download JPEG 3. Download PNG 4. Download PDF |  |  | Pass
5 | Export all the option one by one to verify file should be Exported in each format | 1. File should be Exported in each format 2. Option list should be closed |  |  | Pass
END
US:WEB-7387_TC 22 | Verify the Content of Excel exported file |  |  |  | Test Case Status: | Pass
Precondition | User have SMART URL with valid Login credential.
Step | Action | Expected Result | Dataset | Requirement # | Step Result | Comments
1 | Verify Home screen. | User should on Home screen of the application. Home screen should contain below section: 1. Numerator logo on Top Left side of screen 2. Report list on left side 3. Total creatives chart 4. Search & Export button on left side 5. Schedule and Reset button 6. Saved search list 7. Breadcrumb below creative summary chart 8. Summary tag as per current date filter 9. Field options, Export & Search options button on Right bottom side |  |  | Pass
2 | Verify Chart card | User should be able to see following things on Chart 1. Title of chart 2. Expand,Export & Schedule button on right side 3. Chart graph 4. Legends on Below side 5. Date Range and "Numerator" text on Bottom |  |  | Pass
3 | Click on Export icon | User should be able to see following things 1. Download Excel 2. Download JPEG 3. Download PNG 4. Download PDF |  |  | Pass
4 | Click on "Download Excel" option | 1. File should be Exported in Excel format 2. Option list should be closed |  |  | Pass
5 | Verify Content of exported Excel file | 1. Data should be according to the chart 2. Option list should be closed |  |  | Pass
END
US:WEB-7387_TC 23 | Verify User able to Export Pivot data |  |  |  | Test Case Status: | Pass
Precondition | User have SMART URL with valid Login credential.
Step | Action | Expected Result | Dataset | Requirement # | Step Result | Comments
1 | Verify Home screen. | User should on Home screen of the application. Home screen should contain below section: 1. Numerator logo on Top Left side of screen 2. Report list on left side 3. Total creatives chart 4. Search & Export button on left side 5. Schedule and Reset button 6. Saved search list 7. Breadcrumb below creative summary chart 8. Summary tag as per current date filter 9. Field options, Export & Search options button on Right bottom side | User account - Brand Canada Report - Print report by Category |  | Pass
2 | Verify Pivot | User should be able to see following things on Pivot 1. Download options button 2. Pivot Options button 3. Class,company & division column in pivot 4. All categories in pivot |  |  | Pass
3 | Click Download options | List should be open & user should be able to see following things 1. Download Grid (Default Enabled) 2. Create analert (Default Disabled) 3. View Selected (Default Disabled) 4. Reset Selected (Default Disabled) |  |  | Pass
4 | Click on "Download Grid" option | File should be Exported in Excel Format |  |  | Pass
END
US:WEB-7387_TC 24 | Verify The “Select an Export Type ...“ small modal has a preview of the export. It should cycle as the user changes the export type |  |  |  | Test Case Status: | Pass
Precondition | User have SMART URL with valid Login credential.
Step | Action | Expected Result | Dataset | Requirement # | Step Result | Comments
1 | Verify Home screen. | User should on Home screen of the application. Home screen should contain below section: 1. Numerator logo on Top Left side of screen 2. Report list on left side 3. Total creatives chart 4. Search & Export button on left side 5. Schedule and Reset button 6. Saved search list 7. Breadcrumb below creative summary chart 8. Summary tag as per current date filter 9. Export & Search options button on Right bottom side |  |  | Pass
2 | Verify Export FAB button is fixed on the bottom right of the screen | User should be able to see the Export FAB button on the bottom right of the screen |  |  | Pass
3 | Select "Export FAB" Button | User should be able to open a small modal window on clicking "Export FAB" button with Export options, cancel and Send buttons |  |  | Pass
4 | Verify the opened small modal window with Export options | User should be able to see modal window with Export options of Data Reports, Power Point reports and creative Assets report with the preview beside them , Cancel and Send button |  |  | Pass
5 | Verify The “Select an Export Type ...“ small modal has a preview of the export | User should able to see the preview of the format chosen by the him/her for the export beside the Export options |  |  | Pass
END
US:WEB-7387_TC 25 | Verify Exported video file should not be exported as Image |  |  |  | Test Case Status: | Fail
Precondition | User have SMART URL with valid Login credential.
Step | Action | Expected Result | Dataset | Requirement # | Step Result | Comments
1 | Verify Home screen. | User should on Home screen of the application. Home screen should contain below section: 1. Numerator logo on Top Left side of screen 2. Report list on left side 3. Total creatives chart 4. Search & Export button on left side 5. Schedule and Reset button 6. Saved search list 7. Breadcrumb below creative summary chart 8. Summary tag as per current date filter 9. Export & Search options button on Right bottom side | Ac : Brand - QA Testing weekly report |  | Pass
2 | Click on search options | Select "Online video" option from media |  |  | Pass
3 | Click on apply button | "Online video" media type data should be displayed in AgGrid |  |  | Pass
4 | Now select any record and click on Export button | Export window should be open |  |  | Pass
5 | Select Creative Asset option & click on send buton | 1. File should be Exported 2. Extract the expored file & open the folder 3. Exported file should not be image |  |  | Fail
END
US:WEB-7387_TC 26 | Verify Help Center link in exported excels and PPT should be redirects to new help link |  |  |  | Test Case Status: | Fail
Precondition | User have SMART URL with valid Login credential.
Step | Action | Expected Result | Dataset | Requirement # | Step Result | Comments
1 | Verify Home screen. | User should on Home screen of the application. Home screen should contain below section: 1. Numerator logo on Top Left side of screen 2. Report list on left side 3. Total creatives chart 4. Search & Export button on left side 5. Schedule and Reset button 6. Saved search list 7. Breadcrumb below creative summary chart 8. Summary tag as per current date filter 9. Export & Search options button on Right bottom side | Ac : Brand - QA Testing weekly report |  | Pass
2 | Click on Export button then Select option Ad list XLS & Click on send button | 1. File should be exported 2. Open the file and verify help link should be redirect to "https://help.www2.numerator.com/en/" |  |  | Pass
3 | Now Click on Export button then Select option "1 Creative / Slide" & click on send button | 1. File should be exported 2. Open the file and verify help link should be redirect to "https://help.www2.numerator.com/en/" |  |  | Fail | We have ticket for old help link is displayed in PPT file
END
Home