## Index
Test Case Result Modules-Wise
Module\Status | Count Of Test Case(Steps) |  |  |  |  | % Completed
| Pass | Fail | Blocked | Not Executed | Total
Redesign - Search Options | 27 | 1 | 0 | 0 | 28 | 100%
Total | 27 | 1 | 0 | 0 | 28 | 100%
[5 empty] | % Incompleted | 0%

## Test Scenarios
US# | TC# | Scenario
| TC01 | Verify Search options Floating button at the bottom right corner
| TC02 | Verify Search Modal when no filters are applied
| TC03 | Verify Search Modal when filters are applied
| TC04 | Verify Search Modal when Saved Search is applied
| TC05 | Verify Search options in the summary tags
| TC06 | Verify the tooltip of Search button
| TC07 | Verify Ad Status Search Option | UA : Brand
| TC08 | Verify Date Range Search option
| TC09 | Verify Default options in Date Range search option
| TC10 | Verify Custom Range Filter in Date Range Search option
| TC11 | Verify Day , Week, Month, Quarter and Year options in Date Range Search option
| TC12 | Verify Media Search option
| TC13 | Verify Advertiser Product Search option
| TC14 | Verify Category Search option
| TC15 | Verify Market Search option
| TC16 | Verify Apply button in Search Modal
| TC17 | Verify Reset All button in Search Modal
| TC18 | Verify Cancel button in Search Modal
| TC19 | Verify the Load More functionality in Search Modal
| TC20 | Verify Keyword search option | UA : Brand Canada
| TC21 | Verify the Ad Code search option
| TC22 | Verify the Company Division Brand Search option
| TC23 | Verify the Category Class Search option
| TC24 | Verify the Language Search option
| TC25 | Verify the Clearance Search option
| TC26 | Verify the Coop Advertisers Search option
| TC27 | Verify the Media outlet Search option
| TC28 | Verify clicking the Search option name should show its description

## Search Options
| Name: | Search options |  |  | Regression
| Description: | As a smart user has ability to understand how they can apply search options as per their requirements |  |  | Test Date:
| Product: | Redesign-SMART |  |  | Tester Name: | Nikita Dave
| Feature: | Search options |  |  | OS/Browser: | FF , IE11 , Chrome
| Requirement Covered: |  |  |  | Test Result
| Last Update of this Document: | 2019-12-19 |  |  | Pass | 27
| Estimated Run Time: |  |  |  | Fail | 1
| Author: | Numerator QA Team |  |  | Blocked | 0
| Last Run: |  |  |  | Not Executed | 0
| Test Cases Passed: | 27
| Test Cases Failed: | 1
| Test Cases Blocked: | 0
| Test Cases Not Executed: | 0
User Story: SMART- Search options functionality
Description : As a SMART User, I want to have the ability to understand how to apply search options
US:WEB-7626_TC 01 | Verify Search options Floating button at the bottom right corner | Verify Search options Floating button at the bottom right corner | Verify Search options Floating button at the bottom right corner | Verify Search options Floating button at the bottom right corner | Test Case Status: | Pass
Precondition | User have SMART URL with valid Login credential.
Step | Action | Expected Result | Dataset | Requirement # | Step Result | Comments
1 | Verify Home screen. | User should on Home screen of the application. Home screen should contain below section: 1. Numerator logo on Top Left side of screen 2. Report list on left side 3. Total creatives chart 4. Saved search list 5. Default Summary tags 6. Save and Reset button should be displayed as Disabled on Right side 7. Breadcrumb below creative SavedSearchList 8. Export Result & Search options button on Right bottom side | UA: Brand Report : QA Testing - Brand - Dashboard |  | Pass
2 | Click on Search button at the bottom right corner | 1.A search options Modal window should open with All fields as per the Account and Report selected 2. Modal window should display search options with Cancel, Apply and Reset All button |  |  | Pass
END
US:WEB-7626_TC 02 | Verify Search Modal when no filters are applied | Verify Search Modal when no filters are applied | Verify Search Modal when no filters are applied | Verify Search Modal when no filters are applied | Test Case Status: | Pass
Precondition | User have SMART URL with valid Login credential.
Step | Action | Expected Result | Dataset | Requirement # | Step Result | Comments
1 | Verify Home screen. | User should on Home screen of the application. Home screen should contain below section: 1. Numerator logo on Top Left side of screen 2. Report list on left side 3. Total creatives chart 4. Saved search list 5. Default Summary tags 6. Save and Reset button should be displayed as Disabled on Right side 7. Breadcrumb below creative SavedSearchList 8. Export Result & Search options button on Right bottom side |  |  | Pass
2 | Click on Search button at the bottom right corner | 1.A search options Modal window should open with All fields as per the Account and Report selected |  |  | Pass
3 | Verify the Search Modal window | Search Modal window should show below Fields in "All Fields" Tab 1) Ad Status with options: i) Breaking Ads ii) Running Ads (Default Selected) 2) Date Range with options as per Selected Report, For the given Data set Default option selected should be Last 7 days 3) Media (by Default all options should be selected) 4) Advertiser Product (by Default all options should be selected) 5) Category (by Default all options should be selected) 6) Market (by Default all options should be selected) - Individual associated tabs should also be displayed for respective options beside "All Fields" tab 2. Modal window should display search options with Cancel, Apply and Reset All button |  |  | Pass
4 | Verify All fields tag | Default All fields tag should be displayed as Selected |  |  | Pass
END
US:WEB-7626_TC 03 | Verify Search Modal when filters are applied | Verify Search Modal when filters are applied | Verify Search Modal when filters are applied | Verify Search Modal when filters are applied | Test Case Status: | Pass
Precondition | User have SMART URL with valid Login credential.
Step | Action | Expected Result | Dataset | Requirement # | Step Result | Comments
1 | Verify Home screen. | User should on Home screen of the application. Home screen should contain below section: 1. Numerator logo on Top Left side of screen 2. Report list on left side 3. Total creatives chart 4. Saved search list 5. Default Summary tags 6. Save and Reset button should be displayed as Disabled on Right side 7. Breadcrumb below creative SavedSearchList 8. Export Result & Search options button on Right bottom side |  |  | Pass
2 | Click on Search button at the bottom right corner | 1.A search options Modal window should open with All fields as per the Account and Report selected 2. Modal window should display search options with Cancel, Apply and Reset All button |  |  | Pass
3 | Select Some of the search options and Apply | 1. The Selected options of Respective Fields should be highlighted in the search Modal 2. Reset All, Apply and Cancel button should be Enabled |  |  | Pass
END
US:WEB-7626_TC 04 | Verify Search Modal when Saved Search is applied |  |  |  | Test Case Status: | Pass
Precondition | User have SMART URL with valid Login credential. User should have at least one saved search
Step | Action | Expected Result | Dataset | Requirement # | Step Result | Comments
1 | Verify Home screen. | User should on Home screen of the application. Home screen should contain below section: 1. Numerator logo on Top Left side of screen 2. Report list on left side 3. Total creatives chart 4. Saved search list 5. Default Summary tags 6. Save and Reset button should be displayed as Disabled on Right side 7. Breadcrumb below creative SavedSearchList 8. Export Result & Search options button on Right bottom side |  |  | Pass
2 | Apply any saved search | Saved Search should be applied |  |  | Pass
3 | Verify the Search Modal window | 1.The applied Filters in the saved search should be highlighted in the Search modal 2.Reset All button should be Disabled 3.Apply and Cancel button should be Enabled |  |  | Pass
END
US:WEB-7626_TC 05 | Verify Search options in the summary tags | Verify Search options in the summary tags | Verify Search options in the summary tags | Verify Search options in the summary tags | Test Case Status: | Pass
Precondition | User have SMART URL with valid Login credential.
Step | Action | Expected Result | Dataset | Requirement # | Step Result | Comments
1 | Verify Home screen. | User should on Home screen of the application. Home screen should contain below section: 1. Numerator logo on Top Left side of screen 2. Report list on left side 3. Total creatives chart 4. Saved search list 5. Default Summary tags 6. Save and Reset button should be displayed as Disabled on Right side 7. Breadcrumb below creative SavedSearchList 8. Export Result & Search options button on Right bottom side |  |  | Pass
2 | Click on the Search options summary tags | 1. A search options Modal window should open with All fields as per the Account and Report selected 2. Modal window should display search options with Cancel, Apply and Reset All button |  |  | Pass
END
US:WEB-7626_TC 06 | Verify the tooltip of Search button | Verify, Make default saved search functionality | Verify, Make default saved search functionality | Verify, Make default saved search functionality | Test Case Status: | Pass
Precondition | User have SMART URL with valid Login credential.
Step | Action | Expected Result | Dataset | Requirement # | Step Result | Comments
1 | Verify Home screen. | User should on Home screen of the application. Home screen should contain below section: 1. Numerator logo on Top Left side of screen 2. Report list on left side 3. Total creatives chart 4. Saved search list 5. Default Summary tags 6. Save and Reset button should be displayed as Disabled on Right side 7. Breadcrumb below creative SavedSearchList 8. Export Result & Search options button on Right bottom side |  |  | Pass
2 | Hover on the Search button at the Right bottom corner | The search button should display tooltip - Search Options |  |  | Pass
END
US:WEB-7626_TC 07 | Verify Ad Status Search Option | Verify Ad Status Search Option | Verify Ad Status Search Option | Verify Ad Status Search Option | Test Case Status: | Pass
Precondition | User have SMART URL with valid Login credential.
Step | Action | Expected Result | Dataset | Requirement # | Step Result | Comments
1 | Verify Home screen. | User should on Home screen of the application. Home screen should contain below section: 1. Numerator logo on Top Left side of screen 2. Report list on left side 3. Total creatives chart 4. Saved search list 5. Default Summary tags 6. Save and Reset button should be displayed as Disabled on Right side 7. Breadcrumb below creative SavedSearchList 8. Export Result & Search options button on Right bottom side |  |  | Pass
2 | Click on Search button at the bottom right corner | 1.A search options Modal window should open with All fields as per the Account and Report selected 2. Modal window should display search options with Cancel, Apply and Reset All button |  |  | Pass
3 | Verify Ad Status Search Option in All tabs as well as in its individual tab | 1. Ad Status search option should be displayed in All Fields tab with below options i) Breaking Ads ii) Running Ads (Default Selected) 2. Ad status associated Tab should be available beside the All fields tab 3. Moving to the Ad Status Tab, The tab should only show the options of Ad Status i.e. i) Breaking Ads ii) Running Ads (Default Selected) The selected option should be highlighted and Radio button should be selected 4.User should be able to select any option from the Ad status 5. On selecting and changing the default option, the Reset All button should be Enabled 6. The search should be filtered as per the selection made by the user |  |  | Pass
4 | Select any option other then the default selected | 1. Option should be selected and Highlighted 2.On selecting and changing the default option, the Reset All button should be Enabled 3.The search should be filtered as per the selection made by the user |  |  | Pass
END
US:WEB-7626_TC 08 | Verify Date Range Search option | Verify Date Range Search option | Verify Date Range Search option | Verify Date Range Search option | Test Case Status: | Pass
Precondition | User have SMART URL with valid Login credential.
Step | Action | Expected Result | Dataset | Requirement # | Step Result | Comments
1 | Verify Home screen. | User should on Home screen of the application. Home screen should contain below section: 1. Numerator logo on Top Left side of screen 2. Report list on left side 3. Total creatives chart 4. Saved search list 5. Default Summary tags 6. Save and Reset button should be displayed as Disabled on Right side 7. Breadcrumb below creative SavedSearchList 8. Export Result & Search options button on Right bottom side |  |  | Pass
2 | Click on Search button at the bottom right corner | 1.A search options Modal window should open with All fields as per the Account and Report selected 2. Modal window should display search options with Cancel, Apply and Reset All button |  |  | Pass
3 | Verify Date Range Search option in All tabs as well as in its individual tab | 1) User should be able to see the default options of Date range as per the selected, with that should be able to see the 2 sections showing calendar through which user can select the range as per their requirement 2) User should be able to see the Day, Week, Month, Quarter and Year options above the Calendar 3) Default Selected option should be highlighted both in options as well as in the calendar 4) Calendar should show the drop down options of Months and Year also Arrows for Previous and Next 5)Its individual tab should only show options regarding the Date Range |  |  | Pass
END
US:WEB-7626_TC 09 | Verify Default options in Date Range search option | Verify Default options in Date Range search option | Verify Default options in Date Range search option | Verify Default options in Date Range search option | Test Case Status: | Pass
Precondition | User have SMART URL with valid Login credential.
Step | Action | Expected Result | Dataset | Requirement # | Step Result | Comments
1 | Verify Home screen. | User should on Home screen of the application. Home screen should contain below section: 1. Numerator logo on Top Left side of screen 2. Report list on left side 3. Total creatives chart 4. Saved search list 5. Default Summary tags 6. Save and Reset button should be displayed as Disabled on Right side 7. Breadcrumb below creative SavedSearchList 8. Export Result & Search options button on Right bottom side |  |  | Pass
2 | Click on Search button at the bottom right corner | 1.A search options Modal window should open with All fields as per the Account and Report selected 2. Modal window should display search options with Cancel, Apply and Reset All button |  |  | Pass
3 | Verify Date Range Search option | 1) User should be able to see the default options of Date range as per the selected, with that should be able to see the 2 sections showing calendar through which user can select the range as per their requirement 2) User should be able to see the Day, Week, Month, Quarter and Month options above the Calendar 3) Default Selected option should be highlighted both in options as well as in the calendar |  |  | Pass
4 | Verify Default options in Date Range search option in All Fields tab as well as in its individual tab | 1.User should be able to see below default options: i) Custom Range ii) Today iii) Yesterday iv) Last 7 Days( Default selected) v) Last 14 Days vi) Last Month | UA: Brand Report : QA Testing - Brand - Dashboard |  | Pass
5 | Select any Default option and Apply | 1) Last Month option should be highlighted 2) Calendar should highlight the date range of Last Month 3) Last Month data should be filtered in the Report | Select : Last Month option |  | Pass
END
US:WEB-7626_TC 10 | Verify Custom Range Filter in Date Range Search option | Verify Custom Range Filter in Date Range Search option | Verify Custom Range Filter in Date Range Search option | Verify Custom Range Filter in Date Range Search option | Test Case Status: | Pass
Precondition | User have SMART URL with valid Login credential.
Step | Action | Expected Result | Dataset | Requirement # | Step Result | Comments
1 | Verify Home screen. | User should on Home screen of the application. Home screen should contain below section: 1. Numerator logo on Top Left side of screen 2. Report list on left side 3. Total creatives chart 4. Saved search list 5. Default Summary tags 6. Save and Reset button should be displayed as Disabled on Right side 7. Breadcrumb below creative SavedSearchList 8. Export Result & Search options button on Right bottom side |  |  | Pass
2 | Click on Search button at the bottom right corner | 1.A search options Modal window should open with All fields as per the Account and Report selected 2. Modal window should display search options with Cancel, Apply and Reset All button |  |  | Pass
3 | Verify Date Range Search option | 1) User should be able to see the default options of Date range as per the selected, with that should be able to see the 2 sections showing calendar through which user can select the range as per their requirement 2) User should be able to see the Day, Week, Month, Quarter and Month options above the Calendar 3) Default Selected option should be highlighted both in options as well as in the calendar |  |  | Pass
4 | Verify Default options in Date Range search option in All Fields tab as well as in its individual tab | 1.User should be able to see below default options: i) Custom Range ii) Today iii) Yesterday iv) Last 7 Days( Default selected) v) Last 14 Days vi) Last Month |  |  | Pass
5 | Select the Custom Range option & date | 1. User should be able to select the Custom Range option 2. User should select the Custom range as per their requirement in the Calendar given beside the options 3. Calendar should show drop down list of Months and Year | Date : 1 Dec 2019 to 1 Jan 2020 |  | Pass
6 | Click on Apply | The data should be filtered in the Report as per the custom Range selected by the User |  |  | Pass
END
US:WEB-7626_TC 11 | Verify Day , Week, Month, Quarter and Year options in Date Range Search option | Verify Day , Week, Month, Quarter and Year options in Date Range Search option | Verify Day , Week, Month, Quarter and Year options in Date Range Search option | Verify Day , Week, Month, Quarter and Year options in Date Range Search option | Test Case Status: | Fail
Precondition | User have SMART URL with valid Login credential.
Step | Action | Expected Result | Dataset | Requirement # | Step Result | Comments
1 | Verify Home screen. | User should on Home screen of the application. Home screen should contain below section: 1. Numerator logo on Top Left side of screen 2. Report list on left side 3. Total creatives chart 4. Saved search list 5. Default Summary tags 6. Save and Reset button should be displayed as Disabled on Right side 7. Breadcrumb below creative SavedSearchList 8. Export Result & Search options button on Right bottom side |  |  | Pass
2 | Click on Search button at the bottom right corner | 1.A search options Modal window should open with All fields as per the Account and Report selected 2. Modal window should display search options with Cancel, Apply and Reset All button |  |  | Pass
3 | Verify Date Range Search option | 1) User should be able to see the default options of Date range as per the selected, with that should be able to see the 2 sections showing calendar through which user can select the range as per their requirement 2) User should be able to see the Day, Week, Month, Quarter and Month options above the Calendar 3) Default Selected option should be highlighted both in options as well as in the calendar |  |  | Pass
4 | Verify the day option above the Calendar | 1. The Custom range should be selected 2. User should be able to select day wise range from the Calendar |  |  | Fail | Verify it in both All fields tab as well as its individual tab
5 | Verify the Week option above the Calendar | 1. The Custom range should be selected 2. User should be able to select Weekly date range from the Calendar |  |  | Fail
6 | Verify the Monthly option above the Calendar | 1. The Custom range should be selected 2. User should be able to select date range Monthly from the Calendar |  |  | Fail
7 | Verify the Quarter option above the Calendar | 1. The Custom range should be selected 2. User should be able to select date range in Quarters from the Calendar |  |  | Fail
8 | Verify the Yearly option above the Calendar | 1. The Custom range should be selected 2. User should be able to select date range Yearly from the Calendar |  |  | Fail
END
US:WEB-7626_TC 12 | Verify Media Search option | Verify Media Search option | Verify Media Search option | Verify Media Search option | Test Case Status: | Pass
Precondition | User have SMART URL with valid Login credential.
Step | Action | Expected Result | Dataset | Requirement # | Step Result | Comments
1 | Verify Home screen. | User should on Home screen of the application. Home screen should contain below section: 1. Numerator logo on Top Left side of screen 2. Report list on left side 3. Total creatives chart 4. Saved search list 5. Default Summary tags 6. Save and Reset button should be displayed as Disabled on Right side 7. Breadcrumb below creative SavedSearchList 8. Export Result & Search options button on Right bottom side |  |  | Pass
2 | Click on Search button at the bottom right corner | 1.A search options Modal window should open with All fields as per the Account and Report selected 2. Modal window should display search options with Cancel, Apply and Reset All button |  |  | Pass
3 | Verify the Media option in All tabs and In its individual tab | 1. Media should show options - Television, Print, Radio, Online Display, Online video, Mobile, Outdoor, opt-in Email 2. By default no options should be selected 3. Individual tab of Media should only show options of Media |  |  | Pass
4 | Select any option from Media and Apply | 1. Option should be selected and Highlighted 2. By selecting any option, the Reset All button should be Enabled 3. The search should be filtered as per the selection made by the user |  |  | Pass
END
US:WEB-7626_TC 13 | Verify Advertiser Product Search option | Verify Media Search option | Verify Media Search option | Verify Media Search option | Test Case Status: | Pass
Precondition | User have SMART URL with valid Login credential.
Step | Action | Expected Result | Dataset | Requirement # | Step Result | Comments
1 | Verify Home screen. | User should on Home screen of the application. Home screen should contain below section: 1. Numerator logo on Top Left side of screen 2. Report list on left side 3. Total creatives chart 4. Saved search list 5. Default Summary tags 6. Save and Reset button should be displayed as Disabled on Right side 7. Breadcrumb below creative SavedSearchList 8. Export Result & Search options button on Right bottom side |  |  | Pass
2 | Click on Search button at the bottom right corner | 1.A search options Modal window should open with All fields as per the Account and Report selected 2. Modal window should display search options with Cancel, Apply and Reset All button |  |  | Pass
3 | Verify the Advertiser Product Search option in All tabs and In its individual tab | 1. Advertiser Product search should a search bar to Filter Advertiser product with Selected Displayed and Exclude button 2. It should show options of all advertiser products with Load More button 3. Individual tab of Advertiser Product Search should only show options of Advertiser Product |  |  | Pass
4 | Select option/options and Apply | 1. User should be able to select multiple options 2. Options should be selected and highlighted 3.Reset All button should be Enabled 4. On Applying, the data of the report should be filtered as per the selected options |  |  | Pass
END
US:WEB-7626_TC 14 | Verify Category Search option | Verify Category Search option | Verify Category Search option | Verify Category Search option | Test Case Status: | Pass
Precondition | User have SMART URL with valid Login credential.
Step | Action | Expected Result | Dataset | Requirement # | Step Result | Comments
1 | Verify Home screen. | User should on Home screen of the application. Home screen should contain below section: 1. Numerator logo on Top Left side of screen 2. Report list on left side 3. Total creatives chart 4. Saved search list 5. Default Summary tags 6. Save and Reset button should be displayed as Disabled on Right side 7. Breadcrumb below creative SavedSearchList 8. Export Result & Search options button on Right bottom side |  |  | Pass
2 | Click on Search button at the bottom right corner | 1.A search options Modal window should open with All fields as per the Account and Report selected 2. Modal window should display search options with Cancel, Apply and Reset All button |  |  | Pass
3 | Verify the Category Search option in All tabs and In its individual tab | 1. User should be able to see the Category options for the creatives i.e. Beverages 2. Individual tab of category search option should only show category options |  |  | Pass
4 | Click on any category and Apply | 1. User should be able to select the Category options 2. The option should be selected and highlighted 3.On Applying, the Report data should be filtered as per the category selected | Beverages: juices |  | Pass
END
US:WEB-7626_TC 15 | Verify Market Search option | Verify Market Search option | Verify Market Search option | Verify Market Search option | Test Case Status: | Pass
Precondition | User have SMART URL with valid Login credential.
Step | Action | Expected Result | Dataset | Requirement # | Step Result | Comments
1 | Verify Home screen. | User should on Home screen of the application. Home screen should contain below section: 1. Numerator logo on Top Left side of screen 2. Report list on left side 3. Total creatives chart 4. Saved search list 5. Default Summary tags 6. Save and Reset button should be displayed as Disabled on Right side 7. Breadcrumb below creative SavedSearchList 8. Export Result & Search options button on Right bottom side |  |  | Pass
2 | Click on Search button at the bottom right corner | 1.A search options Modal window should open with All fields as per the Account and Report selected 2. Modal window should display search options with Cancel, Apply and Reset All button |  |  | Pass
3 | Verify the Market Search option in All tabs and In its individual tab | 1.Market search should a search bar to Filter Market options with Selected Displayed and Exclude button 2. It should show options of all Markets with Load More button 3. Individual tab of Market Search should only show options of Advertiser Product |  |  | Pass
4 | Click on option/options of Market and Apply | 1. User should be able to select the Market options 2. The option should be selected and highlighted 3.On Applying, the Report data should be filtered as per the options selected |  |  | Pass
END
US:WEB-7626_TC 16 | Verify Apply button in Search Modal | Verify Market Search option | Verify Market Search option | Verify Market Search option | Test Case Status: | Pass
Precondition | User have SMART URL with valid Login credential.
Step | Action | Expected Result | Dataset | Requirement # | Step Result | Comments
1 | Verify Home screen. | User should on Home screen of the application. Home screen should contain below section: 1. Numerator logo on Top Left side of screen 2. Report list on left side 3. Total creatives chart 4. Saved search list 5. Default Summary tags 6. Save and Reset button should be displayed as Disabled on Right side 7. Breadcrumb below creative SavedSearchList 8. Export Result & Search options button on Right bottom side |  |  | Pass
2 | Click on Search button at the bottom right corner | 1.A search options Modal window should open with All fields as per the Account and Report selected 2. Modal window should display search options with Cancel, Apply and Reset All button |  |  | Pass
3 | Select any options from the search options | 1.User should be able to select the search options as per their requirements 2. The selected options should be highlighted |  |  | Pass
4 | Click on Apply button | The Filters selected by the user should be applied on the report data on clicking the Apply button |  |  | Pass
END
US:WEB-7626_TC 17 | Verify Reset All button in Search Modal | Verify Market Search option | Verify Market Search option | Verify Market Search option | Test Case Status: | Pass
Precondition | User have SMART URL with valid Login credential.
Step | Action | Expected Result | Dataset | Requirement # | Step Result | Comments
1 | Verify Home screen. | User should on Home screen of the application. Home screen should contain below section: 1. Numerator logo on Top Left side of screen 2. Report list on left side 3. Total creatives chart 4. Saved search list 5. Default Summary tags 6. Save and Reset button should be displayed as Disabled on Right side 7. Breadcrumb below creative SavedSearchList 8. Export Result & Search options button on Right bottom side |  |  | Pass
2 | Click on Search button at the bottom right corner | 1.A search options Modal window should open with All fields as per the Account and Report selected 2. Modal window should display search options with Cancel, Apply and Reset All button |  |  | Pass
3 | Verify the Reset all button when no changes are made to the search modal | The Reset all button should disabled |  |  | Pass
4 | Select Filters/options from the Search Modal | The options should be Selected and Reset All button should be Enabled |  |  | Pass
5 | Select Reset All button | All the options selected should be Reset to the default options |  |  | Pass
END
US:WEB-7626_TC 18 | Verify Cancel button in Search Modal | Verify Cancel button in Search Modal | Verify Cancel button in Search Modal | Verify Cancel button in Search Modal | Test Case Status: | Pass
Precondition | User have SMART URL with valid Login credential.
Step | Action | Expected Result | Dataset | Requirement # | Step Result | Comments
1 | Verify Home screen. | User should on Home screen of the application. Home screen should contain below section: 1. Numerator logo on Top Left side of screen 2. Report list on left side 3. Total creatives chart 4. Saved search list 5. Default Summary tags 6. Save and Reset button should be displayed as Disabled on Right side 7. Breadcrumb below creative SavedSearchList 8. Export Result & Search options button on Right bottom side |  |  | Pass
2 | Click on Search button at the bottom right corner | 1.A search options Modal window should open with All fields as per the Account and Report selected 2. Modal window should display search options with Cancel, Apply and Reset All button |  |  | Pass
3 | Click on the Cancel button | The Search options Modal window should be closed |  |  | Pass
END
US:WEB-7626_TC 19 | Verify the Load More functionality in Search Modal | Verify the Load More functionality in Search Modal | Verify the Load More functionality in Search Modal | Verify the Load More functionality in Search Modal | Test Case Status: | Pass
Precondition | User have SMART URL with valid Login credential.
Step | Action | Expected Result | Dataset | Requirement # | Step Result | Comments
1 | Verify Home screen. | User should on Home screen of the application. Home screen should contain below section: 1. Numerator logo on Top Left side of screen 2. Report list on left side 3. Total creatives chart 4. Saved search list 5. Default Summary tags 6. Save and Reset button should be displayed as Disabled on Right side 7. Breadcrumb below creative SavedSearchList 8. Export Result & Search options button on Right bottom side |  |  | Pass
2 | Click on Search button at the bottom right corner | 1.A search options Modal window should open with All fields as per the Account and Report selected 2. Modal window should display search options with Cancel, Apply and Reset All button |  |  | Pass
3 | Verify the search options with Load More button | User should be able to see the load more button at the bottom of the options | Search option- Market |  | Pass
4 | Click on the Load More button | 1. More options associated to the search option should be loaded on screen and should be selectable |  |  | Pass
END
US:WEB-7626_TC 20 | Verify Keyword search option | Verify Keyword search option | Verify Keyword search option | Verify Keyword search option | Test Case Status: | Pass
Precondition | User have SMART URL with valid Login credential.
Step | Action | Expected Result | Dataset | Requirement # | Step Result | Comments
1 | Verify Home screen. | User should on Home screen of the application. Home screen should contain below section: 1. Numerator logo on Top Left side of screen 2. Report list on left side 3. Total creatives chart 4. Saved search list 5. Default Summary tags 6. Save and Reset button should be displayed as Disabled on Right side 7. Breadcrumb below creative SavedSearchList 8. Export Result & Search options button on Right bottom side | UA: Brand Canada Report : Print Dynamics Dashboard (Occurrence) |  | Pass
2 | Click on Search button at the bottom right corner | 1.A search options Modal window should open with All fields as per the Account and Report selected 2. Modal window should display search options with Cancel, Apply and Reset All button |  |  | Pass
3 | Verify the Keyword Search option in All tabs and In its individual tab | 1.Keyword search should have a search bar with text - Filter results by keyword.. 2. Options i.e. All Fields, Headline, Lead Text, Visual, Description should be displayed with radio buttons 3. By Default, All fields option should be selected and Highlighted 4. Individual tab of Keyword should only show options of Keyword search |  |  | Pass
4 | Enter any keyword in the Filter bar and Apply | 1. User should be able to enter keyword in the Filter bar 2. User should be able to select the option where keyword needs to be finds 3. On Applying, data should be filtered as per the keyword searched by the user |  |  | Pass
END
US:WEB-7626_TC 21 | Verify the Ad Code search option | Verify the Ad Code search option | Verify the Ad Code search option | Verify the Ad Code search option | Test Case Status: | Pass
Precondition | User have SMART URL with valid Login credential.
Step | Action | Expected Result | Dataset | Requirement # | Step Result | Comments
1 | Verify Home screen. | User should on Home screen of the application. Home screen should contain below section: 1. Numerator logo on Top Left side of screen 2. Report list on left side 3. Total creatives chart 4. Saved search list 5. Default Summary tags 6. Save and Reset button should be displayed as Disabled on Right side 7. Breadcrumb below creative SavedSearchList 8. Export Result & Search options button on Right bottom side | UA: Brand Canada Report : Print Dynamics Dashboard (Occurrence) |  | Pass
2 | Click on Search button at the bottom right corner | 1.A search options Modal window should open with All fields as per the Account and Report selected 2. Modal window should display search options with Cancel, Apply and Reset All button |  |  | Pass
3 | Verify the AdCode Search option in All tabs and In its individual tab | 1. User should be able to see the Field where user can enter the Adcode of the creatives to filter 2. Multiple Adcodes can be entered and searched by applying space between the Adcodes 3.Individual tab of AdCode should only show options of AdCode search |  |  | Pass
4 | Apply any Adcode and Apply | 1.User should be able to enter one or more AdCodes of the creatives in the AdCode field. 2.On Applying, the data should be searched/filtered as per the Adcode applied |  |  | Pass
END
US:WEB-7626_TC 22 | Verify the Company Division Brand Search option | Verify the Company Division Brand Search option | Verify the Company Division Brand Search option | Verify the Company Division Brand Search option | Test Case Status: | Pass
Precondition | User have SMART URL with valid Login credential.
Step | Action | Expected Result | Dataset | Requirement # | Step Result | Comments
1 | Verify Home screen. | User should on Home screen of the application. Home screen should contain below section: 1. Numerator logo on Top Left side of screen 2. Report list on left side 3. Total creatives chart 4. Saved search list 5. Default Summary tags 6. Save and Reset button should be displayed as Disabled on Right side 7. Breadcrumb below creative SavedSearchList 8. Export Result & Search options button on Right bottom side | UA: Brand Canada Report : Print Dynamics Dashboard (Occurrence) |  | Pass
2 | Click on Search button at the bottom right corner | 1.A search options Modal window should open with All fields as per the Account and Report selected 2. Modal window should display search options with Cancel, Apply and Reset All button |  |  | Pass
3 | Verify the Company Division Brand Search option in All tabs and In its individual tab | 1. Company Division Brand search should a search bar to Filter Company Division Brand with Selected Displayed and Exclude button 2. It should show options of all Company Division Brand with Load More button 3. Individual tab of Advertiser Product Search should only show options of Advertiser Product |  |  | Pass
4 | Select option/options of Company Division Brand and Apply | 1.User should be able to select multiple options. 2. The selected options should be highlighted and displayed in right side 3. On Applying, The Records of the Report should be filtered as per the options selected by the user |  |  | Pass
END
US:WEB-7626_TC 23 | Verify the Category Class Search option | Verify the Category Class Search option | Verify the Category Class Search option | Verify the Category Class Search option | Test Case Status: | Pass
Precondition | User have SMART URL with valid Login credential.
Step | Action | Expected Result | Dataset | Requirement # | Step Result | Comments
1 | Verify Home screen. | User should on Home screen of the application. Home screen should contain below section: 1. Numerator logo on Top Left side of screen 2. Report list on left side 3. Total creatives chart 4. Saved search list 5. Default Summary tags 6. Save and Reset button should be displayed as Disabled on Right side 7. Breadcrumb below creative SavedSearchList 8. Export Result & Search options button on Right bottom side | UA: Brand Canada Report : Print Dynamics Dashboard (Occurrence) |  | Pass
2 | Click on Search button at the bottom right corner | 1.A search options Modal window should open with All fields as per the Account and Report selected 2. Modal window should display search options with Cancel, Apply and Reset All button |  |  | Pass
3 | Verify the Category Class Search option in All tabs and in its individual tab | 1. Category Class search should a search bar to Filter Category Class with Selected Displayed and Exclude button 2. It should show options of all Category Class with Load More button 3. Individual tab of Category Class Search should only show options of Category Class |  |  | Pass
4 | Select option/options of Category Class and Apply | 1.User should be able to select multiple options. 2. The selected options should be highlighted and displayed in right side 3. On Applying, The Records of the Report should be filtered as per the options selected by the user |  |  | Pass
END
US:WEB-7626_TC 24 | Verify the Language Search option | Verify the Language Search option | Verify the Language Search option | Verify the Language Search option | Test Case Status: | Pass
Precondition | User have SMART URL with valid Login credential.
Step | Action | Expected Result | Dataset | Requirement # | Step Result | Comments
1 | Verify Home screen. | User should on Home screen of the application. Home screen should contain below section: 1. Numerator logo on Top Left side of screen 2. Report list on left side 3. Total creatives chart 4. Saved search list 5. Default Summary tags 6. Save and Reset button should be displayed as Disabled on Right side 7. Breadcrumb below creative SavedSearchList 8. Export Result & Search options button on Right bottom side | UA: Brand Canada Report : Print Dynamics Dashboard (Occurrence) |  | Pass
2 | Click on Search button at the bottom right corner | 1.A search options Modal window should open with All fields as per the Account and Report selected 2. Modal window should display search options with Cancel, Apply and Reset All button |  |  | Pass
3 | Verify the Language Search option in All tabs and in its individual tab | 1. User should be Able to see the Language options 2. By Default All options should be selected 3.Individual tab of Language Search should only show options of Language |  |  | Pass
4 | Select option/options | 1.User should be able to select multiple options 2.The selected option should be highlighted 3. Records should be filtered in the report as per the option selected by the User |  |  | Pass
END
US:WEB-7626_TC 25 | Verify the Clearance Search option | Verify the Clerance Search option | Verify the Clerance Search option | Verify the Clerance Search option | Test Case Status: | Pass
Precondition | User have SMART URL with valid Login credential.
Step | Action | Expected Result | Dataset | Requirement # | Step Result | Comments
1 | Verify Home screen. | User should on Home screen of the application. Home screen should contain below section: 1. Numerator logo on Top Left side of screen 2. Report list on left side 3. Total creatives chart 4. Saved search list 5. Default Summary tags 6. Save and Reset button should be displayed as Disabled on Right side 7. Breadcrumb below creative SavedSearchList 8. Export Result & Search options button on Right bottom side | UA: Brand Canada Report : Print Dynamics Dashboard (Occurrence) |  | Pass
2 | Click on Search button at the bottom right corner | 1.A search options Modal window should open with All fields as per the Account and Report selected 2. Modal window should display search options with Cancel, Apply and Reset All button |  |  | Pass
3 | Verify the Clearance Search option in All tabs and in its individual tab | 1. User should be Able to see the Clearance options 2. By Default All options should be selected 3. Individual tab of Clearance Search should only show options of Clearance |  |  | Pass
4 | Select option/options | 1.User should be able to select multiple options 2.The selected option should be highlighted 3. Records should be filtered in the report as per the option selected by the User |  |  | Pass
END
US:WEB-7626_TC 26 | Verify the Coop Advertisers Search option | Verify the Coop Advertisers Search option | Verify the Coop Advertisers Search option | Verify the Coop Advertisers Search option | Test Case Status: | Pass
Precondition | User have SMART URL with valid Login credential.
Step | Action | Expected Result | Dataset | Requirement # | Step Result | Comments
1 | Verify Home screen. | User should on Home screen of the application. Home screen should contain below section: 1. Numerator logo on Top Left side of screen 2. Report list on left side 3. Total creatives chart 4. Saved search list 5. Default Summary tags 6. Save and Reset button should be displayed as Disabled on Right side 7. Breadcrumb below creative SavedSearchList 8. Export Result & Search options button on Right bottom side | UA: Brand Canada Report : Print Dynamics Dashboard (Occurrence) |  | Pass
2 | Click on Search button at the bottom right corner | 1.A search options Modal window should open with All fields as per the Account and Report selected 2. Modal window should display search options with Cancel, Apply and Reset All button |  |  | Pass
3 | Verify the Coop Advertisers Search option in All tabs and in its individual tab | 1.Coop Advertisers search should have a search bar to Filter Coop Advertisers with Selected Displayed and Exclude button 2. It should show options of all Coop Advertisers with Load More button 3. Individual tab of Coop Advertisers Search should only show options of Coop Advertisers |  |  | Pass
4 | Select option/options | 1.User should be able to select multiple options 2.The selected option should be highlighted 3. Records should be filtered in the report as per the option selected by the User |  |  | Pass
END
US:WEB-7626_TC 27 | Verify the Media outlet Search option | Verify the Media outlet Search option | Verify the Media outlet Search option | Verify the Media outlet Search option | Test Case Status: | Pass
Precondition | User have SMART URL with valid Login credential.
Step | Action | Expected Result | Dataset | Requirement # | Step Result | Comments
1 | Verify Home screen. | User should on Home screen of the application. Home screen should contain below section: 1. Numerator logo on Top Left side of screen 2. Report list on left side 3. Total creatives chart 4. Saved search list 5. Default Summary tags 6. Save and Reset button should be displayed as Disabled on Right side 7. Breadcrumb below creative SavedSearchList 8. Export Result & Search options button on Right bottom side | UA: Brand Canada Report : Print Dynamics Dashboard (Occurrence) |  | Pass
2 | Click on Search button at the bottom right corner | 1.A search options Modal window should open with All fields as per the Account and Report selected 2. Modal window should display search options with Cancel, Apply and Reset All button |  |  | Pass
3 | Verify the Media Outlet Search option in All tabs and in its individual tab | 1.Media Outlet search should have a search bar to Filter Media Outlets with Selected Displayed and Exclude button 2. It should show options of all Media Outlets with Load More button 3. Individual tab of Media Outlets Search should only show options of Media Outlets |  |  | Pass
4 | Select option/options | 1.User should be able to select multiple options 2.The selected option should be highlighted 3. Records should be filtered in the report as per the option selected by the User |  |  | Pass
END
US:WEB-7626_TC 28 | Verify clicking the Search option name should show its description | Verify clicking the Search option name should show its description | Verify clicking the Search option name should show its description | Verify clicking the Search option name should show its description | Test Case Status: | Pass
Precondition | User have SMART URL with valid Login credential.
Step | Action | Expected Result | Dataset | Requirement # | Step Result | Comments
1 | Verify Home screen. | User should on Home screen of the application. Home screen should contain below section: 1. Numerator logo on Top Left side of screen 2. Report list on left side 3. Total creatives chart 4. Saved search list 5. Default Summary tags 6. Save and Reset button should be displayed as Disabled on Right side 7. Breadcrumb below creative SavedSearchList 8. Export Result & Search options button on Right bottom side | UA: Brand Report : QA Testing - Brand - Dashboard |  | Pass
2 | Click on Search button at the bottom right corner | 1.A search options Modal window should open with All fields as per the Account and Report selected |  |  | Pass
3 | Verify the Search Modal window | Search Modal window should show below Fields in "All Fields" Tab 1) Ad Status with options: i) Breaking Ads ii) Running Ads (Default Selected) 2) Date Range with options as per Selected Report, For the given Data set Default option selected should be Last 7 days 3) Media (by Default all options should be selected) 4) Advertiser Product (by Default all options should be selected) 5) Category (by Default all options should be selected) 6) Market (by Default all options should be selected) - Individual associated tabs should also be displayed for respective options beside "All Fields" tab 2. Modal window should display search options with Cancel, Apply and Reset All button |  |  | Pass
4 | Click on the Search options name or Header | User should be able to see the description regarding the Search Fields | Click - Ad Status |  | Pass
END
Home